## Sheet1
Sprint 4 Burndown Chart
| Sprint ID | Tasks | Initial Estimate | 2007-02-01 | 2008-02-01 | 2009-02-01 | 2010-02-01 | 2012-02-01 | 2013-02-01 | 2017-01-01
|  |  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Sprint 2 Burndown Chart
| 1011 | Detect behavioural drift | 6 | 2 | 1 | 2 | 1
| 1012 | calculate a risk score and apply user-specific thresholds | 9 |  |  | 2 | 3 | 3 | 1
| 1013 | setting trigger alerts when suspicious behaviour is detected | Day 0: 5; Day 5: 3; Day 6: 1; Day 7: 1
| Remaining Effort |  | 20 | 18 | 17 | 13 | 9 | 3 | 1 | 0 | Sprint ID | Tasks | Initial Estimate | 2022-12-01 | 2023-12-01 | 2027-12-01 | 2028-12-01 | 2001-01-01 | 2002-01-01 | 2003-01-01
| Ideal Trend |  | 20 | 17.1429 | 14.2857 | 11.4286 | 8.5714 | 5.7143 | 2.8571 | 0 |  |  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
[11 empty] | 1004 | Feature extraction (keystroke & mouse) | 4 | 1 | 1 | 1 | 1
[15 empty] | 1005 | Current behaviour profile generation | 3 |  |  | 2 | 1
[15 empty] | 1006 | Baseline profile creation | 2 |  |  |  |  | 2
[15 empty] | 1007 | Drift detection logic | 3 | [5 empty] | 2 | 1
[15 empty] | Remaining Effort |  | 12 | 12 | 12 | 10 | 9 | 7 | 5 | 4
[11 empty] | Ideal Trend |  | 12 | 10.2857 | 8.5714 | 6.8571 | 5.1429 | 3.4286 | 1.7143 | 0
Product Backlog
| Backlog ID | User stories
12 | PB1 | As a user, I want to analyse requirements and define the project scope so that the system objectives are clearly identified.
| PB2 | As a user, I want to review existing literature and identify research gaps so that the proposed solution is novel and relevant.
| PB3 | As a user, I want to design the system architecture so that all components interact efficiently and securely.
| PB4 | As a user, I want to set up the backend and development environment so that implementation can begin smoothly.
| PB5 | As a system, I want to generate a baseline behavioural profile representing normal user behaviour.
| PB6 | As a user, I want to extract meaningful behavioural features from raw interaction data.
| PB7 | As a user, I want to generate a baseline behavioural profile representing normal user behaviour.
| PB8 | As a user, I want to create baseline and current behavioural profiles so that normal and abnormal behaviours can be compared.
| PB9 | As a user, I want to detect behavioural drift so that deviations from normal user behaviour are identified in real time.
| PB10 | As a user, I want to apply adaptive learning and trigger alerts so that security responses improve over time.
| PB11 | As a user, I want to test and evaluate the system so that its accuracy and reliability are validated.
| PB12 | As a user, I want to prepare documentation and presentation materials so that the project outcomes are clearly communicated.
| Backlog ID | User Story
| PB1 | As a researcher, I want to analyse the problem domain and define the project scope so that the system objectives are clearly established.
| PB2 | As a researcher, I want to review existing literature on behavioural biometrics and continuous authentication to identify research gaps.
| PB3 | As a developer, I want to design the overall system architecture so that data capture, processing, and decision-making are well structured.
| PB4 | As a developer, I want to set up the frontend and backend environment to support real-time user interaction processing.
| PB5 | As a system, I want to continuously collect keystroke and mouse interaction data during user sessions.
| PB6 | As a system, I want to store and manage behavioural logs securely for analysis and profiling.
| PB7 | As a system, I want to extract meaningful behavioural features from raw interaction data.
| PB8 | As a system, I want to generate baseline and current behavioural profiles for each user.
| PB9 | As a system, I want to detect behavioural drift by comparing current behaviour with baseline behaviour.
| PB10 | As a system, I want to calculate a risk score and apply user-specific thresholds for authentication decisions.
| PB11 | As a system, I want to trigger alerts when suspicious behaviour is detected without overwhelming the user.
| PB12 | As a system, I want to adapt to long-term behavioural changes through controlled learning mechanisms.
| PB13 | As a system, I want to support multiple users with independent behavioural profiles and thresholds.
| PB14 | As a developer, I want to visualise authentication status and system decisions through a dashboard.
| PB15 | As a researcher, I want to evaluate system performance using security and usability metrics.